## Learning goals
Hour registration Nils Meijer EC2MV.Ea
Learning goal 1 | Date | From-to | Hours | Activity | Learning goal 2 | Date | From-to | Hours | Activity
(Web game) | 2021-12-15 | 19.00 - 21.00 | 2 | Starting project, setting up Three.js | (Unreal Engine) | 2021-12-15 | 12.30 - 14.45 | 2.25 | Exploring UE5, creating scripts
| 2021-12-16 | 17.00 - 18.00 | 1 | Creating basic player controller |  | 2021-12-21 | 8.45 - 12.00 | 3.25 | Worked on character controller
| 2021-12-17 | 14.00 - 15.00 | 1 | Working on movement |  | 2021-12-22 | 15.45 - 17.00 | 1.25 | Implemented box trigger
| 2021-12-20 | 9.45 - 11.30 | 1.75 | Working on movement |  | 2022-01-04 | 10.30 - 12.00 | 2 | Restarted in template project (remade trigger box & widget)
| 2021-12-20 | 13.30 - 16.00 | 2.5 | Fixed movement (left/right) |  | 2022-01-04 | 16.00 - 17.00 | 1 | Started level design
| 2021-12-21 | 19.30 - 20.30 | 1 | Trying to add Physi.js (physics lib) |  | 2022-01-05 | 9.30 - 13.00 | 3.5 | Worked on level
| 2021-12-22 | 9.30 - 12.00 | 2.5 | Added Cannon.js (other physics lib) |  | 2022-01-05 | 15.30 - 17.00 | 1.5 | Worked on level
| 2021-12-22 | 13.15 - 15.00 | 1.75 | Implementing physics |  | 2022-01-06 | 10.30 - 12.30 | 2 | Worked on level
| 2022-01-11 | 13.30 - 16.00 | 2.5 | After a (too) long break from this LO, trying to implement physics again |  | 2022-01-06 | 18.00 - 21.00 | 3 | Recreated project after crash
| 2022-01-12 | 13.00 - 18.30 | 5.5 | Implemented physics, jumping, cleaned up code |  | 2022-01-07 | 10.30 - 13.00 | 2.5 | Continuing level
| 2022-01-13 | 13.00 - 16.00 | 3.5 | Worked on level |  | 2022-01-07 | 22.00 - 23.00 | 1 | Worked on level (puzzle)
[6 empty] | 2022-01-08 | 21.00 - 23.00 | 2 | Implemented first puzzle
[6 empty] | 2022-01-09 | 21.45 - 22.45 | 1 | Implemented game over trigger
[6 empty] | 2022-01-10 | 10.30 - 13.00 | 2.5 | Added lava
[6 empty] | 2022-01-12 | 9.00 - 12.30 | 3.5 | Worked on level
[6 empty] | 2022-01-13 | 8.30 - 12.00 | 3.5 | Worked on level
|  |  | 25 |  |  |  |  | 35.75